Life Safety / Security System Testing Procedures

System Verification and Functional Performance Test Flow Chart

FIRE SPRINKLER				FIRE ALARM				ELEVATORS				SECURITY

System Design / Shop Drawings (FSC)

System Design / Shop Drawings (FAC)

System Design / Shop Drawings (VTC)

System Design / Shop Drawings (SC)

Install Equipment and Controls (VTC)

Install Raceway (EC)

Install Raceway (EC)

Install Piping and Equipment (FSC)

Back box Inspection (FAC)

Witness by MDA EH&S

Inspections (MDA)

Permanent power to Equipment (EC) Controls complete (VTC)

Architectural Finishes Complete

Hydro-Testing (FSC)

MDA Witness

Contractor

Corrects

Deficiency

Architectural Finishes Complete

FA Integration Complete (FAC) Security Integration Complete (SC)

Pull Wiring, Install Devices and Terminate Wiring (SC)

PASS

NO

Issues noted in

ISU Log

Pull Wiring, Install Devices and Terminate Wiring (FAC)

Programming and Pre-Testing (SC)

Equipment Startup

(FSC)

YES

Wiring Inspection (FAC)

Witness by MDA EH&S

System Flushing

APPROVED

Completed PFC’s and startup documentation submitted to

CxA for Review

UTPD Connectivity Complete

Permanent power to Equipment (EC) Controls complete for PFC. (FSC)

Completed installation and startup documentation submitted to AHJ for Review

Issues noted in

ISU Log

Contractor Corrects Issues

NO

Contractor and Subs perform pre-startup inspections and document on PFC’s;

PFC’s submitted to CxA for Review

Contractor / VTC issues Request for Acceptance Testing to MDA / AHJ

Contractor / SC issues Request for Acceptance Testing to UTPD

YES

Issues noted in

ISU Log

Contractor issues Request for Startup to MDA

Programming and Pre-Testing (FAC)

ELEVATOR ACCEPTANCE TESTING

(Contractor, VTC, MDA, AHJ)

SECURITY ACCEPTANCE TESTING

(Contractor, SC, UTPD, CxA)

Contractor Corrects

Deficiency and Re-tests with Contractor

Equipment Startup

(FSC)

FUNCTIONAL PERFORMANCE TESTING

(CxA, Contractor, FAC)

PASS

Issues noted in

ISU Log

Contractor

Corrects

Deficiency

NO

APPROVED

FUNCTIONAL PERFORMANCE TESTING

(CxA, Contractor, MDA)

PASS

INTEGRATED

SYSTEMS TEST

(CxA, Contractor, MDA)

SUBSTANTIAL COMPLETION

PASS

PASS

Completed PFC’s and startup documentation submitted to

CxA for Review

YES

Issues noted in

ISU Log

NO

Contractor Corrects Issues

NO

YES

Fire Pump Flow Testing (FSC)

Witness by MDA EH&S

YES

YES

YES

NO

NO

Contractor issues Request for Functional Performance Testing to MDA

Issues noted in

ISU Log)

Contractor Corrects

Deficiency and Re-tests with Contractor

Connect Fire Alarm Panel to MDA Monitoring Services

Glossary:

AHJ		Authority Having Jurisdiction

CxA		Commissioning Authority

EC 		Electrical Contractor

EH&S		Environmental Health & Safety

FAC		Fire Alarm Contractor

FSC		Fire Sprinkler Contractor

ISU		Issues Log

MDA 		MD Anderson

PFC		Prefunctional Checklist

SC		Security Contractor

UTPD		University Texas Police Department

VTC		Vertical Transportation Contractor